## LEAD
COMPLAINT REDRESSAL SYSTEM
Group Number - 2
Team Lead & FrontEnd Lead- Hitasha Kakkad
BackEnd Lead- Gunti Gautham,Deepak Gupta

## STATUS TRACK
Project Status Check
Date | EMP ID | Name | Domain (Frontend /Backend /Database Part
2022-06-04 | 2507089 | Gunti Gowtham | Discussion about Project
2022-06-04 | 2504459 | Deepak Gupta | Discussion about Project
2022-06-04 | 2503581 | Gorantla Dinesh Dath | Discussion about Project
2022-06-04 | 2505165 | Hitasha Kakkad | Discussion about Project
2022-06-04 | 2503640 | Boya Deddi Gouthami | Discussion about Project
2022-06-04 | 2505815 | Busamudram Krishna Sai | Discussion about Project
2022-06-04 | 2506591 | Devulapally Rajendra Ruchidar | Discussion about Project
2022-06-04 | 2507824 | Dodla Venkatasai Saketh | Discussion about Project
2022-06-04 | 2506341 | Gaurav Shashikant Jat | Discussion about Project
2022-06-04 | 2507255 | Ganugapati Harsha Vardhan | Discussion about Project
2022-06-05 | 2507089 | Gunti Gowtham | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2504459 | Deepak Gupta | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2503581 | Gorantla Dinesh Dath | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2505165 | Hitasha Kakkad | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2503640 | Boya Deddi Gouthami | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2505815 | Busamudram Krishna Sai | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2506591 | Devulapally Rajendra Ruchidar | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2507824 | Dodla Venkatasai Saketh | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2506341 | Gaurav Shashikant Jat | Flow Chart Discussion and Data Base Schema
2022-06-05 | 2507255 | Ganugapati Harsha Vardhan | Flow Chart Discussion and Data Base Schema
2022-06-06 | 2507089 | Gunti Gowtham | Started working on frontend Part
2022-06-06 | 2504459 | Deepak Gupta | Started working on frontend Part
2022-06-06 | 2503581 | Gorantla Dinesh Dath | Started working on frontend Part
2022-06-06 | 2503640 | Boya Deddi Gouthami | Started working on Backend Part
2022-06-06 | 2505165 | Hitasha Kakkad | Started working on frontend Part
2022-06-06 | 2505815 | Busamudram Krishna Sai | Started working on Backend Part
2022-06-06 | 2506591 | Devulapally Rajendra Ruchidar | Started working on Backend Part
2022-06-06 | 2507824 | Dodla Venkatasai Saketh | Started working on Backend Part
2022-06-06 | 2506341 | Gaurav Shashikant Jat | Started working on Backend Part
2022-06-06 | 2507255 | Ganugapati Harsha Vardhan | Started working on Backend Part
2022-06-07 | 2504459 | Deepak Gupta | Working on Admin Module
2022-06-07 | 2507089 | Gunti Gowtham | Working on Admin Module
2022-06-07 | 2503640 | Boya Deddi Gouthami | Working on Customer Module
2022-06-07 | 2503581 | Gorantla Dinesh Dath | Working on customer module
2022-06-07 | 2506341 | Gaurav Shashikant Jat | Working on Complaint module
2022-06-07 | 2506591 | Devulapally Rajendra Ruchidar | Working on Complaint module
2022-06-08 | 2505815 | Busamudram Krishna Sai | Working on Engineer Module
2022-06-08 | 2505165 | Hitasha Kakkad | Working on Engineer Module
2022-06-08 | 2507255 | Ganugapati Harsha Vardhan | Working on feedback Module
2022-06-08 | 2507824 | Dodla Venkatasai Saketh | Working on feedback Module
2022-06-09 | 2504459 | Deepak Gupta | Working On Junit
2022-06-09 | 2507089 | Gunti Gowtham | Working On Junit
2022-06-09 | 2503640 | Boya Deddi Gouthami | Working On Junit
2022-06-09 | 2505815 | Busamudram Krishna Sai | Working On Junit
2022-06-09 | 2503581 | Gorantla Dinesh Dath | Working on Frontend Error
2022-06-09 | 2506591 | Devulapally Rajendra Ruchidar | Working on Backend Error
2022-06-09 | 2506341 | Gaurav Shashikant Jat | Working on Backend Error
2022-06-09 | 2505165 | Hitasha Kakkad | Working on Integration Part
2022-06-09 | 2507824 | Dodla Venkatasai Saketh | Working on Integration Part
2022-06-09 | 2507255 | Ganugapati Harsha Vardhan | Working on Integration Part
2022-06-10 | 2499841 | Deepak Gupta | Completed Junit
2022-06-10 | 2500947 | Gunti Gowtham | Completed Junit
2022-06-10 | 2496200 | Boya Deddi Gouthami | Completed Junit
2022-06-10 | 2500712 | Busamudram Krishna Sai | Completed Junit
2022-06-10 | 2499858 | Gorantla Dinesh Dath | Completed PPt and Documentation
2022-06-10 | 2498852 | Devulapally Rajendra Ruchidar | Completed PPt and Documentation
2022-06-10 | 2498035 | Hitasha Kakkad | Completed PPt and Documentation
2022-06-10 | 2498384 | Gaurav Shashikant Jat | Completed Integration Part
2022-06-10 | 2500149 | Dodla Venkatasai Saketh | Completed Integration Part
2022-06-10 | 2498308 | Ganugapati Harsha Vardhan | Completed Integration Part

## STATUS MEETING
Status Meeting Group - 02 (VB Batch) |  | Group -2
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collabration
2022-03-06 | 10:30 | Checked | 14:00 | Checked | 17:30 | Checked
2022-06-04 | 10:30 | Checked | 14:00 | Checked | 17:00 | Checked
2022-06-05 | 10:30 | Checked | 13:30 | Checked | 17:30 | Checked
2022-06-06 | 10:30 | Checked | 14:00 | Checked | 17:30 | Checked
2022-06-07 | 10:30 | Checked | 13:00 | Checked | 18:45 | Checked
2022-06-08 | 10:30 | Checked | 14:00 | Checked | 18:00 | Checked
2022-06-09 | 10:30 | Checked | 14:00 | Checked | 17:00 | Checked
2022-06-10 | 10:30 | Checked | 13:30 | Checked | 17:00 | Checked